## Sheet1
Everybody
Mo | [10 empty] | PhosphoView Project Planner
Sheridan
Anastasia
Alisha
Han
TASK | 06-12 Jan 2020 | [6 empty] | 13-19 Jan 2020 | [6 empty] | 20-26 Jan 2020 | [6 empty] | 27 Jan - 02 Feb 2020 | [6 empty] | 03-09 Feb 2020 | [6 empty] | 12-16 Feb 2018
| M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Research on Kinases | bar: 06-12 Jan 2020 M to 06-12 Jan 2020 F
Familiarisation of HTML, Flask and MySQL | bar: 06-12 Jan 2020 M to 06-12 Jan 2020 F
Data Mining - Inhibtors | bar: 06-12 Jan 2020 S to 20-26 Jan 2020 W
Data Mining - Phosphosites | bar: 06-12 Jan 2020 S to 13-19 Jan 2020 S
Data Mining - List of Human Kinases and Protein names/aliases | bar: 06-12 Jan 2020 S to 27 Jan - 02 Feb 2020 F
Data Mining - Subcellular Location | bar: 06-12 Jan 2020 S to 27 Jan - 02 Feb 2020 F
Data Mining - Genomic location of PS | bar: 06-12 Jan 2020 S to 27 Jan - 02 Feb 2020 F
Visualisation Phosphoproteomics Data | bar: 13-19 Jan 2020 M to 20-26 Jan 2020 S
Web Site Design | bar: 13-19 Jan 2020 M to 27 Jan - 02 Feb 2020 T
Creation of Database | bar: 13-19 Jan 2020 M to 20-26 Jan 2020 S
Task of Controller | bar: 20-26 Jan 2020 T to 27 Jan - 02 Feb 2020 S
Individual Webpage Design e.g Genome Browser and Help Page | bar: 20-26 Jan 2020 M to 27 Jan - 02 Feb 2020 M
Documentation | bar: 13-19 Jan 2020 F to 27 Jan - 02 Feb 2020 S
≈
Debugging the app
Deploy on AWS